## Overview
PROJECT TIMELINE — WEBSITE COMPANY PROFILE
PT. Kreasindo Graha Persada (KGP)
Group 2 PPIDK — Fullstack Web Developer ¦ Laravel 11 + Tailwind + Alpine.js
Project Title | Website Company Profile PT. Kreasindo Graha Persada
Client / Mitra | PT. Kreasindo Graha Persada
Team | Ikhlas Putra Pambagyo (UPN Veteran Jatim) · Yasir Rais Habibi (UPN Veteran Jakarta)
Duration | 7 Weeks (1 June 2026 – 19 July 2026)
Team Size | 2 Developers
Tech Stack | Laravel 11 (PHP 8.3), Blade, Tailwind CSS, Alpine.js, MySQL, Vite
AI Chatbot | Hybrid 3-layer: FAQ DB → Gemini API → Grok API (fallback)
Scope | 12 public pages + 1 admin panel (/kgp-panel/masuk), 13 DB tables
Deployment | VPS + Nginx + SSL
PHASE SUMMARY
Phase | Weeks | Start | Finish | Tasks | Focus
Fase 1 — Setup, Database & Design | M1–M2 | 01 Jun 26 | 14 Jun 26 | 5 | Requirements, ERD, UI/UX, Laravel setup
Fase 2 — Halaman Publik | M2–M4 | 08 Jun 26 | 28 Jun 26 | 8 | 12 public Blade pages + portfolio filter
Fase 3 — Panel Admin & CMS | M4–M6 | 22 Jun 26 | 12 Jul 26 | 7 | Admin CRUD all modules + AI chatbot
Fase 4 — QA, Optimasi & Go-Live | M7 | 13 Jul 26 | 19 Jul 26 | 6 | Testing, SEO, security, deploy
TOTAL | 7 Wk |  |  | 26

## Detailed Timeline
DETAILED PROJECT TIMELINE — TASK BREAKDOWN (WBS)
ID | Phase | Task / Sub-task | Owner | Start | Finish | Days | Depends | Deliverable | Status
FASE 1 — SETUP, DATABASE & DESIGN (M1–M2)
1.1 | F1 | Kick-off meeting & requirement gathering with KGP | Both | 2026-06-01 | 2026-06-02 | 2 | - | Meeting notes + scope sign-off | Planned
1.2 | F1 | Analisis kebutuhan + penyusunan SRS | Yasir | 2026-06-02 | 2026-06-04 | 3 | 1.1 | SRS document | Planned
1.3 | F1 | Sitemap & information architecture (12 pages) | Yasir | 2026-06-03 | 2026-06-04 | 2 | 1.2 | Sitemap diagram | Planned
1.4 | F1 | Perancangan database & ERD (13 tabel) | Ikhlas | 2026-06-03 | 2026-06-05 | 3 | 1.2 | ERD diagram | Planned
1.5 | F1 | Laravel 11 setup, Git repo, Breeze, .env | Ikhlas | 2026-06-04 | 2026-06-05 | 2 | - | Base repo on GitHub | Planned
1.6 | F1 | Migration + Seeder (37 proyek + master data) | Ikhlas | 2026-06-05 | 2026-06-07 | 3 | 1.4,1.5 | Migrations + seeders | Planned
1.7 | F1 | UI/UX wireframe & corporate design system (Figma) | Yasir | 2026-06-06 | 2026-06-10 | 5 | 1.3 | Wireframes | Planned
1.8 | F1 | High-fidelity mockup all pages + client approval | Both | 2026-06-10 | 2026-06-14 | 5 | 1.7 | Approved Figma mockup | Planned
1.9 | F1 | Layout Blade master + Tailwind + Alpine.js base | Ikhlas | 2026-06-08 | 2026-06-11 | 4 | 1.5 | Master layout | Planned
FASE 2 — HALAMAN PUBLIK (M2–M4)
2.1 | F2 | Halaman Beranda (hero, counter 37+, featured) | Ikhlas | 2026-06-14 | 2026-06-17 | 4 | 1.8,1.9 | Beranda live (staging) | Planned
2.2 | F2 | Halaman Tentang Kami (visi-misi, struktur, legalitas) | Yasir | 2026-06-15 | 2026-06-17 | 3 | 1.8 | Tentang Kami page | Planned
2.3 | F2 | Halaman Layanan IT & Interior (per divisi) | Ikhlas | 2026-06-17 | 2026-06-19 | 3 | 2.1 | Layanan pages | Planned
2.4 | F2 | Halaman Portofolio 37+ proyek + filter divisi | Yasir | 2026-06-18 | 2026-06-22 | 5 | 1.6,2.2 | Portfolio + filter | Planned
2.5 | F2 | Halaman Klien Kami (logo grid per kategori) | Ikhlas | 2026-06-20 | 2026-06-22 | 3 | 2.3 | Klien page | Planned
2.6 | F2 | Halaman Galeri + Lightbox (Alpine.js) | Yasir | 2026-06-22 | 2026-06-24 | 3 | 2.4 | Galeri page | Planned
2.7 | F2 | Halaman Berita & Artikel (list + detail) | Ikhlas | 2026-06-23 | 2026-06-25 | 3 | 2.5 | Berita pages | Planned
2.8 | F2 | Halaman Dokumen Legal (download PDF) + Karir + Kontak | Yasir | 2026-06-25 | 2026-06-28 | 4 | 2.6 | Dokumen/Karir/Kontak | Planned
FASE 3 — PANEL ADMIN & CMS (M4–M6)
3.1 | F3 | Login Admin /kgp-panel/masuk + Dashboard + Auth | Ikhlas | 2026-06-22 | 2026-06-25 | 4 | 1.6 | Secure admin login | Planned
3.2 | F3 | Admin CRUD Layanan IT & Interior | Yasir | 2026-06-25 | 2026-06-28 | 4 | 3.1 | Layanan CRUD | Planned
3.3 | F3 | Admin CRUD Portofolio (multi-foto, featured) | Ikhlas | 2026-06-28 | 2026-07-02 | 5 | 3.1 | Portofolio CRUD | Planned
3.4 | F3 | Admin CRUD Klien + Galeri + Album | Yasir | 2026-07-01 | 2026-07-04 | 4 | 3.2 | Klien/Galeri CRUD | Planned
3.5 | F3 | Chatbot Hybrid: FAQ DB → Gemini API → Grok fallback | Both | 2026-07-02 | 2026-07-09 | 8 | 3.3 | Chatbot live | Planned
3.6 | F3 | Widget Alpine.js + Admin CRUD FAQ & Chat Log | Yasir | 2026-07-06 | 2026-07-10 | 5 | 3.5 | Chat widget + FAQ panel | Planned
3.7 | F3 | Admin CRUD Berita + Dokumen + Karir + Pesan + Settings | Ikhlas | 2026-07-08 | 2026-07-12 | 5 | 3.4 | Remaining CRUD modules | Planned
FASE 4 — QA, OPTIMASI & GO-LIVE (M7)
4.1 | F4 | QA fungsional halaman publik | Yasir | 2026-07-13 | 2026-07-15 | 3 | 3.7 | Public QA report | Planned
4.2 | F4 | QA panel admin + bug fixing | Ikhlas | 2026-07-13 | 2026-07-16 | 4 | 3.7 | Admin QA report | Planned
4.3 | F4 | Optimasi: WebP, lazy-load, Vite bundle (PageSpeed ≥80) | Ikhlas | 2026-07-15 | 2026-07-17 | 3 | 4.1 | Perf score ≥80 | Planned
4.4 | F4 | SEO: meta tag, sitemap.xml, robots.txt | Yasir | 2026-07-16 | 2026-07-17 | 2 | 4.1 | SEO setup | Planned
4.5 | F4 | Keamanan: HTTPS, throttle, session timeout, activity log | Ikhlas | 2026-07-16 | 2026-07-18 | 3 | 4.2 | Security hardening | Planned
4.6 | F4 | Deploy VPS + Nginx + SSL + admin training + go-live | Both | 2026-07-18 | 2026-07-19 | 2 | 4.3,4.4,4.5 | Live site + docs | Planned

## Gantt Chart
GANTT CHART — 7 WEEK SCHEDULE
ID | Task | Owner | M1 1–7 Jun | M2 8–14 Jun | M3 15–21 Jun | M4 22–28 Jun | M5 29 Jun–5 Jul | M6 6–12 Jul | M7 13–19 Jul
FASE 1 — SETUP, DATABASE & DESIGN
1.1 | Kick-off & requirement gathering | Both
1.2 | Analisis kebutuhan + SRS | Yasir
1.3 | Sitemap & IA | Yasir
1.4 | Database design & ERD | Ikhlas
1.5 | Laravel setup, Git, Breeze | Ikhlas
1.6 | Migration + Seeder (37 proyek) | Ikhlas
1.7 | UI/UX wireframe (Figma) | Yasir
1.8 | Hi-fi mockup + client approval | Both
1.9 | Master layout Blade+Tailwind+Alpine | Ikhlas
FASE 2 — HALAMAN PUBLIK
2.1 | Beranda + Tentang Kami | Ikhlas
2.3 | Layanan IT & Interior | Ikhlas
2.4 | Portofolio 37+ + filter | Yasir
2.5 | Klien Kami | Ikhlas
2.6 | Galeri + Lightbox | Yasir
2.7 | Berita & Artikel | Ikhlas
2.8 | Dokumen Legal + Karir + Kontak | Yasir
FASE 3 — PANEL ADMIN & CMS
3.1 | Login admin + Dashboard | Ikhlas
3.2 | CRUD Layanan | Yasir
3.3 | CRUD Portofolio (multi-foto) | Ikhlas
3.4 | CRUD Klien + Galeri | Yasir
3.5 | Chatbot Hybrid (FAQ→Gemini→Grok) | Both
3.6 | Widget + CRUD FAQ & Log | Yasir
3.7 | CRUD Berita+Dokumen+Karir+Settings | Ikhlas
FASE 4 — QA, OPTIMASI & GO-LIVE
4.1 | QA halaman publik | Yasir
4.2 | QA admin + bug fixing | Ikhlas
4.3 | Optimasi performa (PageSpeed≥80) | Ikhlas
4.4 | SEO setup | Yasir
4.5 | Keamanan / hardening | Ikhlas
4.6 | Deploy VPS+SSL + Training + Go-Live | Both
| Legend: | Fase 1 | Fase 2 | Fase 3 | Fase 4

## Milestones
KEY MILESTONES & DELIVERABLES
# | Milestone | Target Date | Acceptance Criteria | Status
1 | SRS + Sitemap + ERD approved | 07 Jun 2026 | Dokumen SRS, sitemap & ERD disetujui klien | Pending
2 | UI/UX mockup approved | 14 Jun 2026 | Mockup Figma semua halaman disetujui klien | Pending
3 | 12 public pages live on staging | 28 Jun 2026 | Semua halaman publik tampil & responsif | Pending
4 | Admin panel functional | 12 Jul 2026 | CRUD semua modul + keamanan berlapis berfungsi | Pending
5 | Chatbot AI hybrid live | 12 Jul 2026 | FAQ→Gemini→Grok menjawab + panel FAQ admin | Pending
6 | QA passed, PageSpeed ≥ 80 | 19 Jul 2026 | Zero blocking bug + skor PageSpeed ≥ 80 | Pending
7 | Go-Live & handover | 19 Jul 2026 | Website live di domain + SSL + training + dokumentasi | Pending

## Improvements
DETAIL IMPROVEMENTS — ENHANCEMENTS BEYOND BASE PLAN
# | Area | Improvement / Refinement | Priority
1 | WBS Granularity | Setiap fase dipecah menjadi sub-task dengan ID, owner, dependency & deliverable | High
2 | Dependency Mapping | Kolom 'Depends' menetapkan urutan kerja agar tidak ada task tumpang tindih | High
3 | Owner Assignment | Pembagian beban kerja eksplisit antar 2 developer (Ikhlas / Yasir / Both) | High
4 | Buffer & Overlap | Fase 2 & 3 dibuat overlap (M4) untuk efisiensi tim 2 orang | Medium
5 | Chatbot Risk | Chatbot dialokasikan 6 hari (M5–M6) karena integrasi 3-lapis paling berisiko | High
6 | Acceptance Criteria | Tiap milestone diberi kriteria penerimaan terukur (mis. PageSpeed ≥ 80) | High
7 | Client Approval Gate | Approval mockup (M2) jadi gate sebelum masuk pengembangan frontend | Medium
8 | Status Tracking | Kolom Status (Planned/In-Progress/Done) untuk monitoring mingguan | Medium
9 | Security Track | QA keamanan dipisah (throttle, session timeout, HTTPS, activity log) | High
10 | Day-level Estimates | Estimasi durasi per task dalam hari (kolom Days) untuk kontrol jadwal | Medium